## Exhaust
Technical Director Info:
Project Description | Exhaust routing
Project Status | ON TIME
Primary Design Goal | 1
Secondary goal(s) | 2, 4, 7
Priority | 1
Note
Project leader info: | Tasin Sayed
Design Completion Deadline | 2022-10-28
Manufacture Deadline | 2022-11-30
Expected Design iterations | 2 | Prototyping intertwined with pure design, cannot be confined to either category
Expected Manufacture Iterations | 1 ideally for primaries, up to 2 for the tertiaries (different muffler positions)
Expected time per design iteration | 1.5 weeks
Expected time per manufacture | 2 weeks | 3 weeks
Likely involvement from others | Aidan, Mete
Extra manufacturing resources | Technician hours for welding \ sponsor machining things for us
Rough project cost | 500
Other comments
Key deadlines
Design iteration 1 | 2022-10-16
Design review | 2022-10-17 | TD (done)
Prototype done | 2022-10-24
Testing done | 2022-11-10 | Driving done - with current muffler arrangement, new tertiaries need manufacturing
Design Review 2 | 2022-11-12 | TD
Final design done | 2022-11-09
Manufacture of final design done | 2022-11-23 | Noise test, quick drive (after muffler configurations manufactured)
Contingency | 2022-11-30

## Gear position
Estimation of timeline for Gear position sensor from Arnav - based on plausibility

## Intake
Technical Director Info:
Project Description | Engine intake
Project Status | ON TIME
Primary Design Goal | 2
Secondary goal(s) | 1, 5, 7
Priority | 1
Notes | Regulatory concern
Project leader info: | Tasin & Mete
Design Completion Deadline | 2022-11-30
Manufacture Deadline | 2023-02-15
Expected Design iterations | 2
Expected Manufacture Iterations | 2
Expected time per design iteration | 2 weeks
Expected time per manufacture | 3 weeks
Likely involvement from others | Aidan & Joel
Extra manufacturing resources | 3D printing
Rough project cost | 150
Other comments | attention to prevent repeat of fbr22 intake incident. not very prototypable, pay attention to not throw money & time out the window
Key deadlines
Design iteration 1 | 2022-10-24
Design review | 2022-10-26
Design iteration 2 | 2022-11-07
Design Review 2 | 2022-11-11 | TD
Final design done | 2022-11-30
Manufacture of final design done | 2023-01-23
Contingency | 2023-02-15

## diff hangers
Technical Director Info:
Project Description | Diff Hangers |  | *Prompt solution, may be re-done as required
Project Status | ON TIME
Primary Design Goal | 2
Secondary goal(s) | 3, 4, 7
Priority | 1
Project leader info: | Tasin Sayed
Design Completion Deadline | 2022-11-09
Manufacture Deadline | 2022-11-30
Expected Design iterations | 3
Expected Manufacture Iterations | 2
Expected time per design iteration | 1-2 weeks
Expected time per manufacture | 1 week
Likely involvement from others | Mete, interested fresher(s)
Extra manufacturing resources | Cutting & machining in Dyson
Rough project cost | 80
Other comments | intertwined with chassis design
Key deadlines
Design discussions | 2022-10-18 | TD (done)
Design iterations 1-2 | 2022-10-28
Design review | 2022-10-30 | TD - meeting slot for Diff hangers
Design iteration 3 | 2022-11-09
Manufacture of final design done | 2022-11-15
Contingency | 2022-11-30

## sprocket
Technical Director Info:
Project Description | Sprocket and Carrier
Project Status | ON TIME
Primary Design Goal | 2
Secondary goal(s) | 1, 3, 6
Priority | 1
Project leader info: | Mete
Design Completion Deadline | 2023-01-01
Manufacture Deadline | 2023-03-10
Expected Design iterations | 3 | (First design iteration is fresher playground, the other two are real)
Expected Manufacture Iterations | 2 | 1 fresher prototype
Expected time per design iteration | 1-2 weeks
Expected time per manufacture | 1-2 weeks
Likely involvement from others | Tasin, interested fresher(s)
Extra manufacturing resources | Cutting & machining in Dyson
Rough project cost | 80
Other comments | Postponed due to diff hanger failure
Key deadlines
Design iterations 1-2 | 2022-11-30
Design review | 2022-12-04
Design iteration 3 done | 2022-12-18
Design Review 2 | 2022-12-23 | TD
Manufacture of final design done | 2023-02-14
Contingency | 2023-03-10

## Rear rad
Technical Director Info:
Project Description | Rear radiator
Project Status | ON TIME
Primary Design Goal | 1
Secondary goal(s) | 2, 6
Priority | 2
Project leader info: | Tasin & Mete
Design Completion Deadline | 2022-11-18 | Can or fluids iterations can trickle into Xmas
Manufacture Deadline | 2023-01-27
Expected Design iterations | 2
Expected Manufacture Iterations | 1
Expected time per design iteration | 2 weeks
Expected time per manufacture | 2 weeks | New parts are required - can be prototyped with current set of tubes
Likely involvement from others | Interested core, Archie, freshers
Extra manufacturing resources | Machining of possible appendices
Rough project cost | 100 | Parts will be necessary - no known psonsorship form Siliconhoses
Other comments | always refer to regs, justify addition
Key deadlines
Design iteration 1 | 2022-10-25
Design review | 2022-10-26
Design iteration 2 done | 2022-11-10
Design Review 2 | 2022-11-11 | ?TD
Final design done | 2022-11-30
Manufacture of final design done | 2022-12-02
Contingency | 2023-01-27

## Chassis bar (incomplete)
Task 1: | Rename the sheet from "Example_Project" to the project name (keep it short, something like "telemetry" or "exhaust"). I'll be collating these into one file later.
Task 2: | Fill in this sheet
Task 3: | Delete these 3 lines such that "Technical Director info:" is on line 1
Technical Director Info:
Project Description | Chassis bar
Project Status | CURRENT UPDATE REQUIRED
Primary Design Goal | 1 | Reliability
Secondary goal(s) | (2) Power Delivery, (3) Development time, (5) Cost
Priority | 1 | (0: Car critical and it currently dosen't exist on the FBR20 eg rectifier. 1: Car critical. We cannot run or get any decent points without this. Stuff like exhaust, tune, uprights.
2: Major points gain but car runs without it just fine eg aero, anti roll bar, moving toe link. 3: Good idea but not super important to car performance eg telemetry
Project leader info: | Tasin Sayed | person in charge of the project (as allocated on idea cards)
Design Completion Deadline | 2023-02-04 | This is design freeze (see calendar on calendar sheet) - big projects that affect the car should be done before this. Exceptions might be made for very small projects but unlikely
Manufacture Deadline | 2023-03-10 | This is when major assembly begins (shifting parts from FBR20 to FBR23) Ideally all projects done here and focus is just on car assembly but again exceptions for small\inconsequential projects.
Expected Design iterations | 4
Expected Manufacture Iterations | 2 | this includes prototypes
Expected time per design iteration | 2 weeks | be realistic here. You are busy with the rest of your life. Rule of thumb is "double it and add 50% compared to the ideal world
Expected time per manufacture | 3 weeks
Likely involvement from others | some core | some core\no input beyond design reviews\big involvement from SLT\likely multi-person project
Extra manufacturing resources | Technician hours for welding \ sponsor machining things for us
Rough project cost | 150 | put a little research into this but don't kill yourself over it. I don’t need it to the nearest pound +-30%\+-£20 is fine
Other comments | might run into major design roadblock if xyz turns out to be true
Key deadlines |  | for you to fill in as you please.Just an example below. These should be the points where it's useful for someone to check in on you, be that me (Aidan) or sub team lead or whatever
Design iterations 1-2 | 2022-10-31
Design review | 2022-12-05 | great to have a couple of these - arrange to chat over the designs you've done with someone to see if they can see any issues or potential for improvement.
Design iteration 3 done | 2022-11-19
Prototype done | 2022-12-03
Testing done | 2023-01-21 | always good to have some mid-project testing - stress test things, play with variables, whatever
Design Review 2 | 2023-01-28
Final design done | 2023-02-04
Manufacture of final design done | 2023-02-25
Contingency | 2023-03-10 | possibly the most important bit of a plan

## Estimation of costs
Item | Source/link | Estimated Cost |  | Further details
Fuel Injectors | https://www.ebay.co.uk/b/Yamaha-Genuine-OE-Motorcycle-Fuel-Jets-and-Injectors/177779/bn_2323144 | Approx. £200 for set of 4, at highest quality
Map Sensor |  | £0 - penty of old Plenums to pull MAP sensor off
Fuel Injectors |  | £70 (4x taking into considering deliver or variations)
Radiator Shut-off Valve | https://uk.rs-online.com/web/p/hose-connectors/5067294?cm_mmc=UK-PLA-DS3A-_-google-_-CSS_UK_EN_Plumbing_%26_Pipeline_Whoop-_-Hose+Connectors_Whoop+(2)-_-5067294&matchtype=&pla-336450067867&cq_src=google_ads&cq_cmp=9771206590&cq_term=&cq_plac=&cq_net=g&cq_plt=gp&gclsrc=ds&gclsrc=ds | Approx. £20 for set of 4
| https://www.ebay.co.uk/itm/124646329429?chn=ps&var=425578763990&_trkparms=ispr%3D1&amdata=enc%3A1Y343ZoYXR9OK7UZzV6tvsA74&norover=1&mkevt=1&mkrid=710-134428-41853-0&mkcid=2&mkscid=101&itemid=425578763990_124646329429&targetid=1647205089320&device=c&mktype=pla&googleloc=1006598&poi=&campaignid=17206177401&mkgroupid=136851690655&rlsatarget=pla-1647205089320&abcId=9300866&merchantid=113804710 | Approx. £30 for 2, might want 1 more for contingency if leaky
Radiator Hose Pipes
New Water Pump | Open it up - check if Calcified, if not too bad no need to replace | https://www.ebay.co.uk/itm/313489823487?var=0&mkevt=1&mkcid=1&mkrid=710-53481-19255-0&campid=5338343596&toolid=10001&customid=eb%3Ax%3Avms%3Aeb%3Ap%3A313489823487%3B | Order of £100 for OEM, decent condition/ £0
Lambda Sensor | https://www.eurocarparts.com/search/710700385 | 30
(Danny suggests current one might be busted, and previous ones too)
HT colorfab |  | £40 - for 700g filament option. I suspect
| Sponsorships: |  |  | Contacted | Status
| 1. Eurocarparts |  |  | Y
| 2. Cooling pipe people |  |  | Y
| 3. Dirtbikesuk |  |  | Y | N
| 4. TE Connectivity |  |  | Y
| 5. Filaments for 3D printing |  |  | Y | Y | Not direct companies - but collaboration with CU3D
| 6. Silicon Hoses |  |  | N | N/Y
| 7. Tube Bender |  |  | N | Y | Dependent on Chassis + If Lister tube quote is too high, could get sections bent by them.